## Slide 2
Quarterly discussion with Housing Leadership Committee Members to discuss progress updates for the DHHS Year 1 Strategic Housing Action Plan.
Welcome & Introductions
Review Year 1 Action Plan
October 20, 2024
4
5
Workgroup Leads Update
Review Plan Implementation Schedule
Public Discussion-Questions
6
Establishing Workgroups
Next Steps/Wrap Up
7

## Slide 3: Review of Implementation Schedule
Public comment period on strategies: Summer 2022
Finalize strategies with stakeholders: August 2022
NCDHHS Leadership reviews strategies: Sept.-Oct. 2022
Drafting NCDHHS Strategic Housing Plan: September-November 2022
NCDHHS Leadership & External Stakeholder Review Committee reviews draft Plan: December - March 2023
Public comment period on full draft Plan: May 2023
Integrate comments/feedback and finalize: July-September 2023
Draft and Finalize Year-One Action Plan: June 2024
Plan launch and start of action plan implementation: August 2024
Josh Walker
Notes: NCDHHS officially launched the plan on August 20th.

## Slide 4: Review of Year 1 Action Plan
  The Year 1 Action Plan is in development progress unto the DHHS NC Strategic Housing Plan website.
  The document contains the strategies for each workgroup
      Development
      Non-Development
      (HSPA) Services
      (ICCHP) Coordination and Partnerships
  Progress updates are made by the 14th of each month
  DHHS will work to upload the document quarterly onto the website to be public facing.
Josh Walker

## Slide 5: Establishing Workgroups
Workgroup | Lead and Co-Leads | TAC Support Staff
Development | Josh Walker josh.walker@dhhs.nc.gov Detra Purcell detra.purcell@dhhs.nc.gov Paul Kimball pekimball@nchfa.com | Jim Yates jyates@tacinc.org
Non-Development | Ken Edminster ken.edminster@dhhs.nc.gov Angela Harper King angela.harperking@dhhs.nc.gov Dr. Latonya Agard latonya.agard@ncceh.org | Matt Leslie mleslie@tacinc.org
(HSPA) Services | Maria Ramirez maria.perez@dhhs.nc.gov Deb Goda deb.goda@dhhs.nc.gov | Jim Yates jyates@tacinc.org
(ICCHP) Coordination & Partnerships | Karen Wade Karen.Wade@dhhs.nc.gov Laura Hogshead laura.hogshead@ncdps.gov | Maseta Dorley mdorley@tacinc.org
Josh Walker

## Slide 6: Workgroup Leads Responsibilities
Lead and coordinate the planning work of the workgroups
Recruit and maintain WG members (8-12 members per WG)
Workgroups led by state staff and community representative (Workgroup Leads)
Workgroups members can include state staff, NC Strategic Plan Housing Leadership Committee members, and other stakeholders
Convene WG call to organize planning work (i.e. schedule/determine cadence of calls)
Track and report on progress in accomplishing Strategies laid out in the Year 1 Action Plan by the 10th of each month
Report progress to HLC (at least quarterly)
Meet periodically with WG leads to support each other’s work
TAC staff acts as support to workgroups and will assist in scheduling, notetaking, facilitation, providing resources and information, and by providing Zoom links for meetings
Josh Walker

## Slide 7: Workgroup Leads Update

## Slide 8: Coordination and Partnerships
Group Activity:
  Meetings – The Coordination and Partnership Workgroup is supported by the ICCHP. Three meetings focused on DHHS Strategic Plan Coordination & Partnership Workgroup goals have occurred: July 12, 2024 provided an overview of the goals, August 12, 2024 focused on roles, responsibilities & coordination with the ICCHP, and September 24, 2024 evaluated progress and prioritized next steps to meet year one goals.
Progress:
  Reviewed the NC Strategic Housing Plan and the Year 1 Action Plan Goals.
Challenges:
  Members supporting the Coordination and Partnership Workgroup also directly support the Hurricane Helene recovery response for the State of North Carolina
Looking Forward
  Conduct October kickoff of the State Agencies Administering Homeless Programs workgroup.
  ICCHP to receive update on HSPA and activate partnerships necessary to support oversight and implementation.
  Launch webpage that will host ICCHP information that can serve as place to disseminate information and have people sign up for mailing list.
Workgroup Leads: Karen Wade and Laura Hogshead
TAC Support: Maseta Dorley
Denise Neunaber

## Slide 9: Development Workgroup
Group Activity:
  Meetings – The Development Workgroup met 9/13/24 to discuss responsibilities of the Co-Leads and the Data Points to Collect and Report on Each Quarter. September 25 was the initial Housing Development Workgroup Kickoff Meeting.
Progress:
  Reviewed the NC Strategic Housing Plan and the Year 1 Action Plan Goals we’ve already started and those to be implemented and our tracking mechanism of all Year 1 Action Plan Goals for Housing Development.
Challenges:
  Identifying a routine cadence, especially given the recent hurricane, devastation and recovery efforts across western NC.
Looking Forward
  Creation of 3,400 new PSH opportunities
  Increased Key Rental Assistance
  HOME-American Rescue Plan (ARP) Programs and increase incentives in SHDP
  PSH Portfolio and known expiring properties/units including HUD 811 PRA portfolio
Workgroup Leads: Josh Walker, Detra Purcell, Paul Kimball
TAC Support: Jim Yates
Josh Walker

## Slide 10: Non-Development Workgroup
Group Activity
  Workgroup has held 4 meetings
  Provided overview and introduction to the plan and workgroup goals to members
Progress
  Created 3 working committees: Admin, Data, and Peer Services
  Started discussing baseline data
  Current efforts underway to partner more effectively with PHA’s for Special Purpose Vouchers, particularly Mainstream vouchers
Challenges
  Not Applicable
Looking Forward
  Working committees will start meeting to strategize on both goals and baseline data
Workgroup Leads: Ken Edminster, Angela Harper King, Dr. Latonya Agard
TAC Support: Matthew Leslie
Ken Edminster/Angela Harper

## Slide 11: Services Workgroup
Group Activity
  NC Housing and Services Partnership Accelerator (HSPA) team have been meeting regularly since early in 2024.
  Member of the NC team attended a national HSPA convening hearing from Federal Partners and other HSPA states to learn about emerging best practices of using Medicaid to support housing-related services and tenancy supports.
Progress
  Working to develop the State’s Permanent Supportive Housing Policy Framework including a definition and models.
  Conducted a services crosswalk of housing and services offered through TCL, Healthy Opportunities, Back at Home and Targeting/Key Programs.
Challenges
  Navigating the demands of Helene disaster response.
Looking Forward
  Finalize PSH Policy Framework including adoption by key State Agencies.
  Analysis of services crosswalk which will create recommendations/next steps to better align eligibility across NC’s programs.
Workgroup Leads: Maria Ramirez and Deb Goda
TAC Support: Jim Yates
Jim Yates

## Slide 12: Public Discussion-Questions
Ann Oshel/Scott Farmer
Notes: Now is the time to hear from our community. We welcome your comments which are very important to us. Because of the call size, we ask that you please remain on mute unless you are speaking. To speak, use the raise hands function to be recognize and come off mute. We appreciate your coming to this meeting. Thank you for attending and sharing your thoughts with us.

## Slide 13: Next Steps
Quarterly meeting schedule for the Housing Leadership Committee. All meetings will be held virtually via the Zoom.gov meeting and open to the general public.
Monday, January 27, 2025 at 10am-11am ET
Monday, April 21, 2025 at 10am-11am ET
Monday, July 21, 2025 at 10am-11am ET
Josh Walker

## Slide 14: Contact
For all questions regarding the Housing Leadership Committee, please reach out to:
Josh Walker, LCMHCS
Olmstead Housing Director
Health Equity Portfolio / Office of the Secretary
NC Department of Health and Human Services
Mobile: 919-618-6733
Josh.walker@dhhs.nc.gov
Josh Walker